## 2026_Town_Dam_Month-to-Date_Wat
Form Completed By: | Date and Time of Check-In | Hwy 557 Ruler | Dam Ruler (N/A when Logs Out) | Is Water Level In Compliance | OOC Comment | Weather (temperature in celsius) | Water Management Plan Period | Type of Check-In | Bay 1: TURBINES | Bay 2: 6 Logs Maximum | Bay 3: 8 Logs Maximum | Bay 4: 10 Logs Maximum | Bay 5: MECH GATE MAX 9 Logs | Bay 1 After change: TURBINES | Bay 2 After change: 6 Logs Maximum | Bay 3 after change: 8 Logs Maximum | Bay 4 after change: 10 Logs Maximum | Bay 5 after change: MECH GATE MAX 9 Logs | Dam Ruler After Log Changes | WATER TEMPERATURE if required
Dana | 2026-04-29 08:30 | 1.15 (approx above gauge) |  | NO | May be a spike in level from rain yesterday, or possibly increasing from upstream water arriving. Notified TBR, MNR, MFN. All logs remain out. | 3C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-28 16:10 | 1.13 (bouncing 1.12-1.14) |  | NO | Holding or close to it. Winds have picked up, so bouncing more so than last check but seems to settle most in same spot as last visit. Centre bolt in pics. Hasn't increased nor dropped since holding yesterday, even with rain today. Hoping to see level resume decline with some cooler evening temps coming up and no rain over 1mm or less until Monday. Also hoping to be able to slow things down from above soon for all sites. | 11C, overcast | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-28 12:59 | 1.13 (above gauge still) |  | NO | holding level from yesterday, even after rain *good sign it may resume a decline after rain is through system, as upstream lakes increased levels from rain (if similar amounts received). Special Weather Statement ended early at 12pm. Team reported ice off Duborne at the 557 corner it is visible from. | 10C, overcast | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-28 06:25 | 1.13, holding.. approx same location as last 2 checks |  | NO | Working through flood conditions in basin while receiving freshet water from upstream on WMP that was held back as much as possible to try to permit lower end to catch up. Heavy rain from weather warning still in effect. Hopefully once rains have flushed through the system, we will see level continue to decline. Will continue to monitor level over the day to provide updates and update MNR to see if we can slow water release from above at all to assist, as Mat has been on a steady decline over last 7 days, (until last nights rain). | 8C, Special Weather Statement 15-25mm rain, Provincial Flood Watch in effect. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-27 19:02 | na - weather update only. Active until April 30/26. Texted to TBR and MFN in addition to the daily report for review. |  | NO | Recovering from Potomac Flood conditions, and working through freshet water levels in the WMP system in addition to forecasted rain. | Provincial Flood Watch for Northwest and Northeast Regions, Watershed Conditions Statement for Southern Region Issued by the Surface Water Monitoring Centre, Ministry of Natural Resources on April 27, 2026, at 5:00 p.m. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-27 16:45 | 1.13 |  | NO | May have been a very small decrease from the morning read (still above the mStaff gauge), but appears to have held. Will monitor to determine if still in a slower decline or if holding before starting to rise again. All logs remain out of dam. | Special Weather Statement in effect; 15-25mm rain. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-27 09:10 |  | .17-.24 | NO | Ruler dam not applicable with all the logs out; see Dana's comments. | 12 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 6
Dana | 2026-04-27 06:45 | 1.13 |  | NO | Continued decline observed. Levels receding and increased flow from upstream passing as well. All logs remain out. | 4C, weather statement in effect ~25mm rain over 24hrs | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-26 11:30 | 1.15 |  | NO | Continued decline observed. Increased flow from upstream reported to begin passing water held back as long as possible for basin to process flood conditions. | 6C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-26 09:24 |  | Moving 20-24 | NO | Freshet. MNR and MFN aware | 5 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 6
Dana | 2026-04-25 11:34 | 1.18 |  | NO | Continued decline observed. All logs remain out of dam since April 10. | 5C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-24 15:36 |  | Moving 24-31 | NO | Freshet. MNR and MFN aware. | 11 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 6
Colin | 2026-04-24 09:25 |  | Moving 25-30 | NO | Freshet and flood warning. TBR, MNR and MFN are aware. | 9 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 6
Dana | 2026-04-24 08:45 | 1.2* approx (corrected on photo review) |  | NO | Back to reading from ruler mount location at approximate level. Has still been on steady decline. Flood warning still in effect. Ruler closer to being visible/able to read. Once I compare photos, if I have to make corrections to a few recent readings, will add an asterisk beside those levels that are changed (switched measurements method at this location due to being above ruler). Ice break up starting from Duborne. Some portions still pretty thick as they broke up at the bridge. Possible ice dam capability if lots comes down the river together. | 8C, | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-23 16:30 | 1.22* corrected on photo review |  | NO | Observing continued decline at steady pace. More water coming down from WMP watershed, as levels above rose in coordinated effort to try to permit the lower end time to process high water re: freshet and Potomac flood condition water. All logs to remain out of dam. Flood warning continues. | 14C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-23 12:03 | N/A |  | NO | Freshet and flood monitoring ongoing. Observations: Level Decreases continue, and warm weather may help to shed more ice from the lakes. More water to come from upstream elevated levels in coordination with MNR and TBR/MFN. Initial Calculations noted that west arm drain may not assist - To be confirmed and coordinated with respective parties if proceeding. | 16C, rain forecasted in upcoming days. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-23 09:34 |  | .35 (33-37) | NO | Freshet and MNR Flood Warning. TBR, MFN, MNR aware. Slowly declining. More water coming from above. All logs remain out of dam. /ds | 7 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 4
Dana | 2026-04-22 17:50 | 1.25* Corrected |  | NO | See prior comment; continued decline at this time with more water to come from upper watershed. Steady decline despite increased water coming from upper watershed, now that flows have slowed from the Potomac flooding. Updated MNR flood warning in effect. All logs remain out of dam. The first 30 logs were removed since April 6, 2026 and the last 3 (1 per bay) we require approval from MNR to remove have been out since April 10, 2026. We will continue to keep dam wide open at this time. West arm may get its overflow drainage route reopened as well which should also assist. | 12C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-22 13:58 |  | .35-.46 (range moving on ruler from current) | NO | Freshet and flood warning. Continued monitoring and reporting. | 12 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 2
Dana | 2026-04-22 06:42 | 1.261 |  | NO | Flood Warning extended yesterday by MNR. Steady decline in this system; increased water levels above in WMP watershed will continue to work down system, Potomac flood contribution has significantly reduced. Rain expected: FRI: 90% 5-10mm, SAT: 80% 1-3mm, MON: 60% 15-20mm, TUE: 40% ~1mm. Continued observation reporting and coordination with TBR, MNR and MFN. All logs remain out of dam since pulled ahead of flood conditions. | -2C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-21 13:40 | 1.318 |  | NO | See previous comment. Declining. Continue reporting observations to TBR, MNR and MFN. | 12C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Greg | 2026-04-21 13:39 |  |  |  |  | 12 sunny | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-21 09:51 |  | 42-56 | NO | Freshet. TBR, MNR and MFN aware. | 7 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 2
Dana | 2026-04-21 07:20 |  | .49 (.46-.55) | NO | See earlier 557 comments. In addition, Potomac no longer crossing road at Village Road, and is slowly receding off the shoulders. Appears on Astles road side to have come down 4-6" approx. Ice break up pieces observed downstream from 557 bridge on return trip, which was great to see. Dock that was floating appears it may be hung up on bottom, but remains too far out to safely secure. SAFETY REPORTING REMINDER - MNR BOOM BROKEN AT TOWN DAM. | 3C | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | Will obtain later visit
Dana | 2026-04-21 05:30 | 1.34 |  | NO | Receding from yesterday, but MNR flood warning still in effect, and lots of water still coming down watershed. MNR BOOM BROKEN at town dam (unsafe to repair in current conditions) - incoming debris that would be stopped with it can make it to dam, as well as watercrafts/people it would hold back. MNR looking to reopen west arm overflow drainage that was eliminated sometime ago. | 2C (Fri 80% ~5mm, Sat 40% <1mm, Sun 40% <1mm, Mon 70% 10-15mm) | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-20 15:31 | 1.38 (down 1cm from last read). |  | NO | Levels are receding, however elevated levels above are beginning to work their way down the system also. Will continue to monitor WMP watershed and report observations to Town of Blind River, Mississauga First Nations and Ministry of Natural Resources. ~5mm at 80% chance updated for Friday forecast. | 5C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-20 15:28 |  | 0.53 | NO | See comments in Dana's reporting re: Freshet. MNR boom broken upstream from dam. (MNR and TBR made aware on discovery on the weekend). | 6 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-20 13:49 |  |  |  |  | 4 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-20 13:03 |  | .55. (.48-.60) | NO | See comments in Dana's reporting re: Freshet. MNR boom broken upstream from dam.. | 4 | Apr. 1 to May 31 *Take Water Temp* | RULER only Dam |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-20 11:00 |  |  |  |  | -1 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-20 10:46 |  |  |  |  | -1 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-20 10:34 |  |  |  |  | -1 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-20 10:22 |  |  |  |  | -1 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-20 09:53 |  | .55 (.50-.60) **reminder MNR Boom Broken upstream from river*** | NO | See comments in Dana's reporting re: Freshet. MNR boom broken upstream from dam. | -4 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 2
Dana | 2026-04-20 09:30 | 1.39 (down 5-8mm) |  | NO | Down 5-8mm from last night. Potomac at Astles still at same level but appears slower moving in passing. Uncertain what upstream from there looks like yet. Cold last night may have helped tighten up some water, but it will help stiffen up the ice caps on the lakes too (water displacement). Coordinated release (log removal) of upstream water will need to be done, per usual with MNR. At this time, as upper lake is high but has peaked, no plan to pull logs yet and will continue at current rate while possible for the basin. Caution should still be maintained, and MNR flood warning is still active. | 0C, was -8C overnight last night. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-19 23:40 |  |  | NO | Freshet |  | Apr. 1 to May 31 *Take Water Temp* | ONSITE only Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-19 19:30 | 1.395-1.3975 (down .5cm from earlier reading). |  | NO | On route to ruler, observed that flooded areas showed subtle signs that water had receded slightly. On arrival to the ruler, .5cm decrease was observed. *Important to note that upstream levels have spiked, and that water is also making its way down the system. Colder temps tonight should assist somewhat. 10-30% rain forecasted Mon-Thu (no accumulation); and 60% of ~5mm Fri at this time. Inquiry to MNR submitted to see if they'll reopen the west arm Huron drainage also. | -1C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-19 18:49 |  |  | NO | Flood Warning and start of Freshet. All observations reported to TBR, MFN and MNR via daily reports and live updates. At the dam the water on ruler spans a large range due to turbulence. Over all it does appear to have come down slightly. Hoping tonight's cold tightens things up further to allow the basin to catch up further. /ds |  | Apr. 1 to May 31 *Take Water Temp* | ONSITE only Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-19 14:05 | ***1.40-1.4025 approx *** (held from 8:54am reading; I re-measured, and although we are over gauge and using a modified system to measure, it appears to have held position. |  | NO | While levels appear to be stabilizing, caution and monitoring will still need to be done as more water must move down the system. I don't know status of Potomac, but will check for changes at Astles bridge on route up stream for the WMP. I'll include that feedback in town dam check as it should have also held or show a lower range if holding or on decline. New graffiti below bridge also.. | 3C, change to forecast Friday; now calling for 60% ~5mm. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-19 09:49 |  | .57 (.50-.65) | NO | Freshet | 0 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #1 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-19 08:54 | 1.40-1.4025 approx (Last reading 1.395-1.3975, up 5-7mm since then.) |  | NO | Continued updates regarding flood conditions in the Blind River. Low lying properties visible from the bridge have water on properties or are slowly being encroached by rising levels. | 2C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-19 04:50 | 1.395-1.3975, approx (.1667cm/hr increase flow rate approx). |  | NO | Still elevated flood conditions in lower basin. MNR flood warning in effect until 22nd so far. Potomac still contributing flood water. WMP upper levels elevated also and more water is making its way down. Behind Eaket, Water has reached the barricade so will need to be adjusted. On the side by Huron St, water is moving towards the road also. The town has Sand available at public works for sand bags and more sandbags are arriving soon. | -1C, chance of snow today (40% <1cm AM and afternoon), 70% ~15mm rain Friday | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-19 01:10 | 1.3875-1.39 |  | NO | Freshet monitoring. Rate of increase has slowed again. | -1C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-18 19:30 | 1.38 approx (up 1cm since 1.37 at 4:40pm. |  | NO | Same as last OOC observation comments. Had donated older sandbags that MFN was able to inspect and possibly put to use. Dropped off to location on River and water levels are well up onto lawn. TBR has some coming. | 3C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-18 16:40 | 1.37 (up 1cm approx since 2:05; approx same rate of increase as last.) |  | NO | Freshet high water. Flood conditions in Potomac initially and now also in the Blind River. MNR flood warning remains active. Barrier up behind highschool boat launch. Coordinating level observation updates from monitoring with TBR, MFN and MNR. Still rising and have not peaked in basin. | 4C, windy | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-18 14:05 | 1.36 (up 1cm in 2.5 hrs = .4cm/hr) approx |  | NO | Up 1cm from 11:30 reading. At the corner closest to Duborne on Hwy 557, we reported high water abutting the road (approx 2' from topping). Will continue to report changes as observed. Water levels elevated above also. Potomac remains in flood condition. | 5C, windy, cold overnight. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge
Dana | 2026-04-18 11:37 | 1.35 (up .5cm from last reading at 7:50am; flow increase currently averaging at .125 cm/hr. |  | NO | Upstream water elevated and working down system also. No additional information available on Potomac status as of yet. Observed flood levels up behind WC Eaket. TBR sending team out to add barricades. TBR advised they have sand available for sand bagging at the public works department for anyone who inquires to fill bags from home hardware. Possible bags available from MNR also but will confirm. MNR Boom break reported by our other team onsite at Town Dam. One Y shaped log is lodged into the point of a pier between bay 4/5. It is pinned and unable to be moved at this time. Will need to monitor for more debris accumulating and try to clear so gain is not plugged so water can continue to pass, especially in absence of boom. MNR aware (broken pieces upstream and some free in Huron). TBR aware as more protection / awareness may be required along the shorelines as the boom is no longer there to rescue boats, people, etc, and stop debris. | 4C. 30% chance rain for the next 3 days. -2 tonight; -7 tomorrow. ~15mm forecasted on 24th at 70% | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-18 07:52 | 1.345 |  | NO | Freshet. Water is by the door of the apartment building by the Dowsy bridge and on the other side the backyard of the brick house is completely under water. | 7 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-18 04:30 | 1.33 approx |  | NO | See town dam check from prior submission this AM. | 8C, rain - rainfall warning in effect. Heavier rain started at 5:03AM, with lighter steady rain prior. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-18 04:10 |  | .45 (moving .42-.48) | NO | See weather re: rainfall statement. We already have localized flooding from unexpected Potomac flooding contribution in addition to the prior rounds of heavy rain. In addition, Lakes had good, thick ice this year and are still covered (prior to rain) and displacing water. Hoping to see break up start soon to assist with levels. Upstream from here, water levels are elevated and rising also and more water will work its way down. | 5C, rain - weather statement "rain, at times heavy, is expected. The ground, already near saturation, has a little ability to absorb further rainfall. Localized flooding is likely. Some roads may become impassible." | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | #2 ON only = 2 Logs Out | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | NA
Dana | 2026-04-17 20:57 | Approx 1.315 |  | NO | Potomac flooding, more freshet to come down from above, flood permanent road closure going into effect at Potomac Bridge at Astles and village road due to erosion and washout (MFN provided me with an update after they patrolled the area). Utility pole that would be affected reported yesterday to hydro also so they could look at it before levels rose if needed. Ice still on lakes, displacing water and hoping they break up soon. Weather statement 20-30mm tonight/tomorrow morning possible. Sending observations to TBR, MFN and MNR. | 9C, weather warning of 20-30mm | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-17 15:00 | 1.305- 1.3075 |  | NO | Freshet. | 15 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge
Zoran | 2026-04-17 14:36 |  |  |  |  | 14 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-17 13:45 |  | 35-41 | NO | Freshet. TBR, MNR and MFN aware. *weather warning of 20-30mm rain* | 15 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 3
Zoran | 2026-04-17 12:01 | Up 1/4-1/2 cm to 1.295-1.2975 approx |  | NO | Freshet. | 15 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge
Colin | 2026-04-17 11:13 |  | 35-45 | NO | Freshet. MNR and MFN aware (in addition to TBR*). | 15 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 3
Colin | 2026-04-17 10:42 |  |  |  |  | 15 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Kevin | 2026-04-17 09:30 | Approx up 1/4cm to 1.2925 |  | NO | Freshet | 9 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-17 05:40 | Up .5-1cm, 1.285-1.29 |  | NO | Monitoring increases to report changes. Request feedback on how much/how far Potomac is backed up as it is surging rapidly. Much faster and higher by a few inches than yesterday. (Utility pole at washout risk reported). Coordinate with MNR on what to expect from above Matinenda still as full freshet is not underway yet. (Snow to surface water mm remaining approx, etc) continue to provide updates to Town of Blind River and MFN and clarify when any further action/planning takes place so I can inform residents what is available and who to contact when they call, as the town has directed them to call me for updates. As far as I know, ice cover still on Duborne, Canoe Lake, Chiblow Lake and Matinenda, which is adding to the elevated levels, causing water to travel faster under it to open areas, and displacing water where it is. Once ice covers melt/let go, we should come down slightly in each lake also. Was -1C at arrival and standing surface water had ice surface again. Not cold enough to slow down moving water, but likely refroze softened ice caps on lakes. Hoping the warmth of the sun assists with breaking it down today. | -1C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-17 03:31 | 1.28, Up 7cm approx since 6:15PM, Texted updates observed again to TBR, MFN, MNR |  | NO | Coordinating with MNR, MFN and TBR. Monitoring continued flood conditions on Potomac & freshet flow coming from upstream (that has not yet fully engaged). Potomac flow has increased substantially. Water over road wider, deeper and flowing faster also. Uncertain how deep the original area has eroded to. Water has expanded to include a utility pole, so I called it into hydro for assessment before more erosion occurs while they can still access and noted to access from Astles on the call. | 1C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-16 18:15 | 1.205-1.21 approx |  | NO |  | 10C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Kevin | 2026-04-16 16:21 | Approx 1.2-1.205 |  | NO | Freshet | 14 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-16 16:00 |  |  |  |  | 10 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-16 15:52 |  |  |  |  | 10 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-16 15:41 |  |  |  |  | 10 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Greg | 2026-04-16 15:24 |  |  |  |  | 11 sunny | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-16 15:22 |  |  |  |  | 13 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Dana | 2026-04-16 15:01 | 1.19- 1.195 |  | NO | Over compliance - freshet.***2:55PM Potomac at Astles/Village road bridge breached from Potomac flooding. Up 1' since last night*** 3:00PM 557 at 1.19-1.195 (increase per hour at .285cm/hr, but may change pending potomac surge. 11:30 AM at 1.18-1.185. 7AM ruler at 1.165. flow increase rate has slowed from past days of 1cm/hr down to approx .41cm/hr. As of approx 9:15AM the level was at approx 1.175, or .5cm / hr increase approx. (as of 14th: 40% <1mm) check by Zk, Jf, update by Dana | 9 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge
Dana | 2026-04-16 14:46 |  |  |  |  | 11c | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Dana | 2026-04-16 14:35 |  | .25 (.21-.29) | NO | Freshet and flood control coordination in progress with MNR, MFN and TBR | 11C | Apr. 1 to May 31 *Take Water Temp* | RULER only Dam |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | NA
Kevin | 2026-04-16 12:13 |  | .25 (.21-.31) | NO | Freshet | 13 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 2
Kevin | 2026-04-16 11:32 | Approx 1.18-1.185 |  | NO | Freshet | 12 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge
Kevin | 2026-04-16 09:17 | [5 empty] | Apr. 1 to May 31 *Take Water Temp* | REMOTE access only
Kevin | 2026-04-16 09:17 | Approximately 1.175 |  | NO | Freshet | 7 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge
Dana | 2026-04-16 07:16 |  | .22 (.19-.25), rising head level | NO | See comment on 557 ruler log | 7C | Apr. 1 to May 31 *Take Water Temp* | RULER only Dam |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | Will obtain later today on deck
Dana | 2026-04-16 07:01 | Approx 1.165, increase flow rate decreased to .41cm/hour. |  | NO | Freshet high water from heavy rains, snow melt, run off, saturated grounds unable to absorb, and flood waters surging into river from Potomac. Inflow rise rate decreasing. | 4C, forecast change: 40% 1-3mm this AM, 60% 1-3mm tomo, *down to 5-10mm at 100%SAT. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-15 21:22 | 1.125, rise slowing, upstream as well, no change from Potomac flood output. |  | NO | Freshet high water from rainfall, snow melt, ground saturation and run off, with surging from Potomac flooding. Emailing levels for all checks daily to TBR, MFN and MNR to track changes, per usual, and for town to share on their website for the public, plus sending team additional update emails during high water. Texting this team between email updates to keep everyone informed. Full spring thaw run off has not fully engaged upstream from the dams yet, that will bring more water to follow in addition to the flooding from the Potomac; Showing signs of stabilizing ahead of that, which is good. | 7C, raining (forecasting 70% of ~1mm), | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-15 18:28 | Approx 1.10-1.11 (approx increase of .66cm/hr, down from prior increase rates). |  | NO | Freshet. Rate of increase starting to slow. Potomac flood conditions flowing steady at this time, but severe flooding from backed up water by ice dams above could add to flows at any point as they release also (like the one that let go and surged into blind river with the last heavy rainfall that was blocked between Astles road and blind river initially). | 10C (12C 30% chance rain tomorrow, 12C 40% chance of 1mm Fri, ***7C 100% chance of 15-20mm rain Saturday*** | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-15 15:24 | 1.09-1.10 (estimated) |  | NO | Over compliance. Freshet. | 11 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-15 15:20 |  |  |  |  | 13 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-15 14:31 |  | Surging from 9 to 15 | NO | Freshet. MNR and MFN have been notified . | 11 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 2
Colin | 2026-04-15 13:50 |  |  |  |  | 11 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-15 13:33 |  |  |  |  | 11 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-15 13:26 |  |  |  |  | 11 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-15 13:23 |  |  |  |  | 11 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-15 13:04 | 1.07- 1.08 (little movement) |  | NO | Over compliance. Freshet. | 11 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-15 10:56 | 103 |  | NO | Over compliance. Freshet. | 9 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-15 10:45 |  |  |  |  | 9 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-15 10:11 |  |  |  |  | 9 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-15 10:00 |  |  |  |  | 8 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Zoran | 2026-04-15 09:39 |  |  |  |  | 8 | Apr. 1 to May 31 *Take Water Temp* | AREA WATER MONITORING
Colin | 2026-04-15 09:15 | 103 |  | NO | Freshet. MNR and MFN are notified | 7 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-15 07:22 |  | .08 approx (heavy current moving from .05 to .11) | NO | Head level rising with freshet. Water on shoreline at dawsy bridge pond as ice broke from shore. Property flooding visible from 557 bridge. Updating TBR, MFN, MNR. Next email goes out at 7:30AM for reporting and updating between reporting periods via text for monitoring and planning. All logs remain out of dam. | 6C | Apr. 1 to May 31 *Take Water Temp* | RULER only Dam |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | Will obtain at check today
Dana | 2026-04-15 07:00 | Approx 1.02-1.03 (last reading of .995 at 2:30AM; rate of increase down at approx .75cm/hr, down from 1cm/hr during yesterday), Headpond level at dam rising. |  | NO | Freshet increase with Potomac flood conditions adding and full ice cover on Duborne and most WMP lakes (causing elevated levels in open areas). Continuing to keep TBR, MFN, MNR informed for action planning. | 6C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-15 03:28 |  | .03 to .06; Head level rising. (Was below ruler yesterday). | NO | Freshet. Coordinating water level updates with TBR, MFN and MNR | 8C | Apr. 1 to May 31 *Take Water Temp* | RULER only Dam |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | NA, will obtain during daylight.
Dana | 2026-04-15 02:34 | .995 (.995-1.00), dawsy bridge pond has let go from shore and water has risen onto shoreline. Behind highschool, level is still below ice surface attached to shoreline, but is visible at the shoreline through open areas of ice also. Potomac at Astles appears at roughly same height as prior checks yesterday, most of the ice cover in the river is now gone also, flood conditions still present and Uncertain of status toward iron bridge from here. |  | NO | Freshet underway with full ice cover on the lake, and surging from flooded heavily flooded Potomac. | 6C, -5mm forecasted today, <1mm tomorrow, ~15mm Saturday | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-14 21:03 | .955 (.9525-.9625) |  | NO | Continued rise at almost 1cm/hr over the last 3 hours. All logs out of dam. Forecast shows a few cooler nights after heavier rain on Sunday, and the following week appears sunnier. | 7C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-14 18:05 | .93 (.925-.935 with current flow) |  | NO | Freshet. Coordinating levels with TBR, MFN and MNR. Potomac in flood conditions surging to blind river also. All logs out at dam. | 10C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-14 15:10 | 90 |  | NO | Freshet. MNR and MFN notified | 10 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-14 12:28 | .875 (.87-.88) |  | NO | Freshet. Coordinating updates with TBR, MNR, MFN. Potomac flood conditions still existing but rapidly moving now from Astles to Blind River. | NA | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-14 12:12 | NA |  | NO | dup entry | NA - dup entry | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-14 09:55 | .85 (.84-.855) |  | NO | Over compliance. Freshet. | 6 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-14 09:14 | Surging from 84 to 85 |  | NO | Freshet. MNR and MFN notified | 7 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Zoran | 2026-04-14 09:12 |  | Under ruler. | NO | Freshet. MNR aware. | 5 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 2
Dana | 2026-04-14 05:49 | .82 (as reported, can only rise in river where open as ice cover fully on Duborne still). 1-3mm forecasted today, -5mm tomorrow, 1-3mm the following day and ~15mm Saturday. Unsure status of Potomac River high water/backed up water reported. Teen temps for next 4 days to hopefully help break up lake ice to allow the water to disperse around the lake instead of just in the river. 8cm up from yesterday, all logs remain out of dam; will update TBR, MFN, MNR) |  | NO | All logs remain out of dam. Only river open from Hudson bridge to mouth of Duborne (free of ice), so that portion of the river is rising (up 8cm from yesterday). Keeping all decision makers informed as we move through freshet. | 4C, rain (weather warning last night also) | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-13 15:41 |  | Below 0 | YES |  | 11 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) | [6 empty] | 3
Colin | 2026-04-13 15:18 | 74 |  | YES |  | 10 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Kevin | 2026-04-13 11:26 | .73-.74 |  | YES |  | 8 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-13 09:37 | 73 |  | YES |  | 9 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-12 17:52 | .72 (plus current movement), *ALL LOGS OUT OF DAM*, Potomac appears backed up at Astles into surrounding Forrest, but is still moving to Blind River |  | YES |  | 4C, rain and weather statement in effect, plus more rain each day for next 5 days. | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-12 08:07 | 0.71 |  | YES |  | 2C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Dana | 2026-04-11 08:08 | 0.69 |  | YES |  | -3C (35-45mm rain tomorrow, all logs out at town dam***) | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-10 15:28 | 68 |  | YES |  | 6 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX)
Colin | 2026-04-10 15:01 |  | Below 0 | YES |  | 4 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX) | Both OFF = NO LOGS OUT | 6 Logs Out (MAX) | 8 Logs Out (MAX) | 10 Logs Out (MAX) | 9 Logs Out (MAX) |  | 2
Dana | 2026-04-10 14:22 | .67-.68, moving w/current ALL LOGS OUT, 35-45mm rain forecasted Sunday, with more rain in days to follow. |  | YES |  | 6C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-10 09:14 | 67 |  | YES |  | 4 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-09 11:35 |  | Below 0 | YES |  | 7 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX) | [6 empty] | 2
Colin | 2026-04-09 11:18 | 64 |  | YES |  | 7 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-09 09:21 | 64 |  | YES |  | 7 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Zoran | 2026-04-08 15:52 | 0.65 |  | YES |  | 1 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-08 11:26 |  | Below 0 | YES |  | 4 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX) | [6 empty] | 2
Colin | 2026-04-08 11:01 | 66 |  | YES |  | 2 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-08 09:15 | 66-67 |  | YES |  | -1 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-07 11:06 | 69 |  | YES |  | -3 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Zoran | 2026-04-07 09:31 |  | Bellow ruler | YES |  | -9 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX) | [6 empty] | 0
Colin | 2026-04-07 09:10 | 69 |  | YES |  | -8 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-06 14:49 | 73 |  | YES |  | 6 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Zoran | 2026-04-06 12:43 | 0.73 |  | YES |  | 2 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-06 11:24 |  | 33 | YES |  | 7 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 4 Logs Out | 5 Logs Out | 5 Logs Out | 9 Logs Out (MAX) | Both OFF = NO LOGS OUT | 5 Logs Out | 7 Logs Out | 9 Logs Out | 9 Logs Out (MAX) | 0 | 4
Dana | 2026-04-06 07:07 | 0.735 |  | YES |  | -4C | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 4 Logs Out | 5 Logs Out | 5 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-05 16:15 | 71 |  | YES |  | 1 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 4 Logs Out | 5 Logs Out | 5 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-05 11:34 | 71 |  | YES |  | 3 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 4 Logs Out | 5 Logs Out | 5 Logs Out | 9 Logs Out (MAX)
Colin | 2026-04-04 08:37 |  | 41 | YES |  | 1 | Apr. 1 to May 31 *Take Water Temp* | ONSITE only Headpond | NO LOGS OUT = Both Off | 4 Logs Out | 5 Logs Out | 5 Logs Out | 5 Logs Out | Both OFF = NO LOGS OUT | 4 Logs Out | 5 Logs Out | 5 Logs Out | 9 Logs Out (MAX) | 32
Colin | 2026-04-04 08:19 | 65 |  | YES |  | 1 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 4 Logs Out | 5 Logs Out | 5 Logs Out | 5 Logs Out
Colin | 2026-04-03 12:19 |  | 43 | NO | Prepping for freshet and up coming weather. | 4 | Apr. 1 to May 31 *Take Water Temp* | ONSITE only Headpond | NO LOGS OUT = Both Off | 4 Logs Out | 5 Logs Out | 5 Logs Out | 3 Logs Out | Both OFF = NO LOGS OUT | 4 Logs Out | 5 Logs Out | 5 Logs Out | 5 Logs Out | 42 | 2
Colin | 2026-04-03 12:03 | 59 |  | NO | Prepping for freshet and up coming weather | 4 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 4 Logs Out | 5 Logs Out | 5 Logs Out | 3 Logs Out
Colin | 2026-04-02 12:19 |  | 34 | NO | Prepping for freshet and upcoming storm. | 2 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 3 Logs Out | 3 Logs Out | 3 Logs Out | 7.5 Logs Out | Both OFF = NO LOGS OUT | 4 Logs Out | 5 Logs Out | 5 Logs Out | 3 Logs Out | 34 | 2
Colin | 2026-04-02 11:15 | 51 |  | NO | Prepping for freshet. | 1 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 3 Logs Out | 3 Logs Out | 3 Logs Out | 7.5 Logs Out
Greg | 2026-04-02 09:21 | 51 |  | No, but only 557 checked so far |  | -1 overcast | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 3 Logs Out | 3 Logs Out | 3 Logs Out | 7.5 Logs Out
Colin | 2026-04-01 15:46 | 51.5 |  | NO | Prepping for freshet | 1 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 3 Logs Out | 3 Logs Out | 3 Logs Out | 7.5 Logs Out
Zoran | 2026-04-01 13:56 | 0.515 |  | NO | Under compliance. Prepping for freshet. | 8 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 3 Logs Out | 3 Logs Out | 3 Logs Out | 6.5 Logs Out
Colin | 2026-04-01 12:48 |  | 39 | NO | Prepping for freshet | -1 | Apr. 1 to May 31 *Take Water Temp* | ONSITE both Headpond & Powerhouse | NO LOGS OUT = Both Off | 3 Logs Out | 3 Logs Out | 3 Logs Out | 6.5 Logs Out | Both OFF = NO LOGS OUT | 3 Logs Out | 3 Logs Out | 3 Logs Out | 7.5 Logs Out | 37 | 2
Colin | 2026-04-01 09:18 | 52 |  | NO | Prepping for freshet | -6 | Apr. 1 to May 31 *Take Water Temp* | RULER only 557 bridge |  | 3 Logs Out | 3 Logs Out | 3 Logs Out | 6.5 Logs Out